- Practical Steps in Sustainable Tourism

- Examples of action from around the world

Water and Energy Saving

in the Hotel Industry in Cyprus

The Issue & the Opportunity

Water supply in Cyprus is provided by a large number of dams and two desalination plants. The total capacity of dams in 2008 was over 325 million cubic meters and the two desalination plants on the island – one in Larnaca and one in Dhekelia - produce about 100,000 cubic meters per day. The desalination plants alone, however, without water from the dams, do not provide the levels of potable water needed on the island.

A leaking water supply system (since 2006, 8 ½ million cubic meters of water was wasted through broken piping), three years of drought and years of the current government’s inability to deal effectively with the issue of water supply on the island resulted in a serious water shortage in the summer of 2008; horrifying pictures of dams with dry cracked earth on the bed were on the daily news together with reports that water reserves would run out within days. Water rationing was introduced in April of 2008, and Cyprus was forced to import water from Greece. The hotel industry and local people felt the pinch of the water shortage and the life of every single resident revolved around water availability.

To respond to this water shortage as it affected the hotel industry, the Cyprus Sustainable Tourism Initiative (CSTI) with the support of the Travel Foundation (UK) and the Cyprus Tourism Organisation undertook the implementation of a 6 month ‘Water and Energy Saving’ project within the hotel industry.

The Action

The aim of the ‘Water and Energy Saving’ project was to reduce the consumption of water and energy in the hotel industry and to assist the industry take collective action that will help the destination begin to address the impact of the Cyprus tourism industry on climate change.

The objectives of the project were to:

- raise awareness in the industry

- distribute educational/training tools

- compile information on existing water and energy saving measures and practices in the hotel industry

- identify and promote water and energy saving best practices

- monitor consumption

- calculate savings

- work with Tour Operators to sensitise visitors about water shortages in Cyprus

- promote Cyprus as a responsible destination.

The Outcome

The projects produced the following:

- 1 Twelve Basic Tips check list

- 1 Monitoring/Consumption Recording Form

- 1 Tour Operators’ letter to hotels

- 4 progress reports

- 1 Final project report

- 1 presentation to the ‘World Travel Market’

- data on water and energy consumption saving in Cyprus

- support letters from the industry

- 4 articles:

-	ABTA Magazine, Sam Lewis: Water, Water Everywhere

-	WWW. Travel Weekly, Opinion: Cyprus backs water-saving scheme.

-	WWW. Travel Weekly, Cyprus Water Shortage

-	The Cyprus Weekly, Demetra Moliva: Cyprus launches water awareness campaign

www.thetravelfoundation.org.uk

Taking Action

What was done:

To implement the objectives of the project CSTI undertook the following activities:

- ensured funding for the needs of the project from the Travel Foundation and the Cyprus Tourism Organisation and hired a project manager

- held consultation meetings with the Water Board, the Government Office for the Environment, the Cyprus Associations of Hotel Managers and the Cyprus Tourist Enterprises Association; these organisations provided support, information and resources for the project

- gave TV/newspaper interviews in order to generate public support for the project

- developed criteria for participating in the project

- scheduled individual and group presentations on the project and project materials

- met with hotel managers, chief engineers and operation directors and presented the project and materials to 106 hotels across the island; these included hotels of different star ratings, categories and locations

- distributed 106 ‘Sustainable Tourism is Good for Business’ Kits and CD-ROM

- circulated 120 Water Board Posters on water saving tips for display in the different hotel departments

- distributed over 10,000 ‘Save Water’ stickers of the Cyprus Association of Hotel Managers for prominent display in hotel bathrooms, public toilets and kitchens

- developed the ‘Twelve Basic Tips’ check list for the collection of data

- developed a form for recording and comparing consumption

- monitored and recorded each hotel’s consumption monthly

- gained commitments of participating hotels

- compiled and analysed data

- presented results to the ‘World Travel Market’ in London.

How it was done:

Hotel Visits: Project Manager set meetings with hotel managers, explained the project and presented training kit, and gained manager’s commitment to participate in the project and provide monthly readings on the consumption of water and energy in their establishment and measures they would undertake to reduce consumption.

Twelve Basic Tips to Make a Difference Check List: The check list was developed in order to facilitate the collection of information on pre-existing water and energy saving measures in participating hotels and to record the measures undertaken by each hotel regarding water/energy conservation after the project was introduced. All hotels committed to taking part in the project agreed to record and submit (to the Project Manager) monthly developments.

Monitoring/Consumption Recording Form: a simple form for recording monthly consumption of water in cubic meters and energy in kilowatt hours together with the number of sleepers was developed. All participating hotels recorded and provided monthly comparative figures for the May – October 2007 and the May – October 2008 periods.

Progress Reports: In order to monitor the progress of the project, the project manager submitted monthly reports to the CSTI monthly Board meeting. The reports included activities undertaken, success or difficulties faced regarding the collection of data from each participating hotel, difficulties faced by participating hotels in implementing measures, saving measures implemented by each establishment, data showing consumption in each hotel, and comments from managers of participating hotels. This allowed the CSTI board to provided input and direction to the project manager. The data on each participating hotel in these reports remains confidential.

Who was involved:

- The Travel Foundation: supported financially the project and provided the ‘Sustainable Tourism is Good for Business’ training kit and CD.

- Cyprus Tourism Organisation: supported financially the project, was part of the coordinating committee and provided 10,000 ‘Save Water” stickers which were distributed to hotels across the island.

- Cyprus Sustainable Tourism Initiative: was responsible for generating support and publicity for the project, giving direction to the project, providing support to  the project staff,  implementing the project activities,  analysing data, and presenting the results to the funders and general public.

- Tour Operators (TUI, Thomas Cook and Sunvil): Tour operators were involved in the project through their participation on the CSTI Board of Directors who gave direction to and oversaw the implementation of the project. Tour Operators also wrote a letter to hotels encouraging them to participate in the project and were involved in informing visitors about the water shortage in Cyprus.

- Hotel industry: 106 hotels (67 hotels participated fully in the project) across the island, their managers and staff.

- Cyprus Tourism Enterprises (STEK): encouraged their members to participate in the project

- Cyprus Hotel Managers Association: provided 10,000 ‘Water is Precious’ stickers which were distributed to hotels across the island and encouraged their members to participate in the project

- Water Board: provided 120 posters on tips on how to save water; the posters were distributed to hotels

- Government Office for the Environment

- University of Nicosia and Intercollege- Hospitality and Tourism Department: assisted with the analysis of data and preparation of report

When it was done:

May to November 2008

Problems Encountered

May to October is the peak tourism season in Cyprus, therefore hotel managers were not easily accessible; locating them, speaking to them directly and setting up appointments was time consuming. Also challenging was the setting up of meetings with hotels in the same area on the same day so as to avoid unnecessary travelling. As well, hotel managers were at first hesitant to provide the information; they did so when they were reassured that the information about specific hotels was confidential and would not be in anyway publicised.

Successes Achieved

The following saving measures were adopted as a result of the project:

-	installation of low flow showers and tap output reducers

-	reduction of the volume of water in the toilet cisterns

-	installation of refrigerator air curtains

-	installation of motion sensors in the less frequently used areas

-	water-flow reduction valves in bathrooms

-	auto-cut units for pool showers

-	delayed action sensors fitted in refrigerators so that compressors do not start the moment doors are opened;

-	magnetic rings on diesel pipes that aid the efficient burning of fuel

-	replacement of 1.5l bottled water with the 1l bottle

-	tent cards in bathrooms that display linen change options

-	key cards for all the rooms.

Other best practices identified:

-	‘Green Teams’ with representatives from each department

-	solar panels

-	many hotels have their own water treatment plants

-	recycling of water that is used for watering gardens

-	steam generators using gas for on-premises laundry

Savings as a result of the project:

From May to October 2008, the project recorded water savings of 131,833m3 in water consumption, or a 10% decrease in consumption. This decrease saved the industry over € 239,000.

With regards to energy reduction and savings, the project recorded a reduction of 925,240 kWh, or a decrease of 1%. This reduction saved the industry over €160,000.

gggg

Best Practice and Lessons Learned

Lessons Learned

- All hotels can make savings on water and energy by taking a few simple low cost initiatives

- The more committed a hotel manager is the better the results

- Even where a hotel had undertaken best practice, savings were still made

- This is a win - win situation; hoteliers save money and help the environment

Key Success Factors

  - The Project Manager (a hotel manager himself, and known to most hoteliers) had easy access to hotel managers; it enabled him to get his foot in the door and introduce the sustainable accommodation pack and its resources

- Cyprus was undergoing a severe water shortage in 2008, so this gave hotels a greater incentive to take action

- Where hotel managers were 100% committed and undertook training with all departments a greater proportion of success in terms of savings was achieved

- The project created a positive competition among hoteliers; something good was happening and they wanted to be part of it

- There was a sense that hoteliers were ready for action and needed someone to lead the way.

Project Risks

- Timing is important.  Because of the nature of the project, results need to be collected during the tourist season when most managers are extremely busy and access to them may be impossible.  Introduction and training should therefore take place before the busy tourist season commences; especially training of key staff

- Where the project is undertaken without a Project Manager, it may be difficult to motivate hotel managers and collect the data.

Relevance to other destinations

- This project can be replicated in any destination.

Useful Resources

N/A

Contact:

Cyprus Sustainable Tourism initiative

P.O.Box 58538, 3735 Limassol

Cyprus

Phone: 99440983

E-mail: info@csti-cyprus.org